## Migration Log
DATE ADDED TO MIGRATION LIST | START DATE | COMPLETION DATE | NOTES | TARGET DATE | OSPC ACCOUNT TENANT ID | SOURCE OF REQUEST | MIGRATION OPERATOR NAME | CUSTOMER NAME | COMPANY NAME | CONTACT NAME | EMAIL | PHONE | BUSINESS OWNER | TECHNICAL OWNER | INDUSTRY | CUSTOMER ID | REGION | TARGET FLEX REGION | PRIORITY RANK | WAVE | FLEX READINESS SCORE | FLEX READINESS | OSPC INFRA SIZE | BUSINESS BLAST RADIUS | STACK CATEGORY | MIGRATION METHOD | SIZE RANK | STATUS | CURRENT STAGE | BUSINESS SYSTEM NAME | BUSINESS SYSTEM TYPE | CRITICALITY | ENVIRONMENT | OSPC VM COUNT | ARCHITECTURE | COMPONENTS Details
2026-07-04 | 2026-07-04 | 2026-07-10 |  | 2026-07-10 | 1342314 | Customer |  | home depot — ERP SpaceX | home depot | jack builder | jack@homedepot.com | 84793215913 | SpaceX |  | erp | 1342314 | SJC — San Jose | SJC — San Jose | 2 | Wave 1 | 95 | FLEX Ready | Large | Core | erp | Rehost | 3 | WAITING LIST |  | ERP SpaceX | erp | Critical | Production | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring | Web Frontend ¦ API Server ¦ ERP Backend ¦ Database ¦ Batch Worker ¦ Queue ¦ File Storage ¦ Reporting ¦ Monitoring
2026-07-04 | 2026-07-04 | 2026-07-10 |  | 2026-07-10 | 1342314 | Customer |  | home depot — Amazon | home depot | jack builder | jack@homedepot.com | 84793215913 | Amazon | Brian | ecommerce | 1342314 | SJC — San Jose | SJC — San Jose | 1 | Wave 1 | 95 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | WAITING LIST |  | Amazon | ecommerce | Critical | Production | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring | Web Frontend ¦ API Gateway ¦ API Server ¦ Product Catalog Backend ¦ Database ¦ Cache ¦ Queue ¦ Payment Connector ¦ Order Worker ¦ Search Service ¦ Monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | Hector | space X — ERP SpaceX | space X | elon musk | elon@starlink | 1222333444 |  |  | erp | 1234 | DFW — Dallas | DFW — Dallas | 2 | Wave 1 | 85 | FLEX Ready | Large | Core | erp | Rehost | 3 | ACTIVE |  | ERP SpaceX | erp |  |  | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | Hector | space X — Amazon | space X | elon musk | elon@starlink | 1222333444 |  |  | ecommerce | 1234 | DFW — Dallas | DFW — Dallas | 1 | Wave 1 | 85 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | ACTIVE |  | Amazon | ecommerce |  |  | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | Stephen | space X — ERP SpaceX | space X | elon musk | elon@starlink | 1222333444 |  |  | erp | 1234 | DFW — Dallas | DFW — Dallas | 2 | Wave 1 | 85 | FLEX Ready | Large | Core | erp | Rehost | 3 | ACTIVE |  | ERP SpaceX | erp |  |  | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | Stephen | space X — Amazon | space X | elon musk | elon@starlink | 1222333444 |  |  | ecommerce | 1234 | DFW — Dallas | DFW — Dallas | 1 | Wave 1 | 85 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | ACTIVE |  | Amazon | ecommerce |  |  | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring
2026-07-04 | 2026-07-04 | 2026-07-11 |  | 2026-07-11 | 1342314 | Customer |  | Starlink — ERP SpaceX | Starlink | Jonh dusk | elon@tesla.com | 1222333444 | SpaceX |  | erp | 1342314 | SJC — San Jose | SJC — San Jose | 2 | Wave 1 | 95 | FLEX Ready | Large | Core | erp | Rehost | 3 | WAITING LIST |  | ERP SpaceX | erp | Critical | Production | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring | Web Frontend ¦ API Server ¦ ERP Backend ¦ Database ¦ Batch Worker ¦ Queue ¦ File Storage ¦ Reporting ¦ Monitoring
2026-07-04 | 2026-07-04 | 2026-07-11 |  | 2026-07-11 | 1342314 | Customer |  | Starlink — Amazon | Starlink | Jonh dusk | elon@tesla.com | 1222333444 | Amazon | Brian | ecommerce | 1342314 | SJC — San Jose | SJC — San Jose | 1 | Wave 1 | 95 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | WAITING LIST |  | Amazon | ecommerce | Critical | Production | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring | Web Frontend ¦ API Gateway ¦ API Server ¦ Product Catalog Backend ¦ Database ¦ Cache ¦ Queue ¦ Payment Connector ¦ Order Worker ¦ Search Service ¦ Monitoring
2026-07-04 | 2026-07-04 | 2026-07-11 |  | 2026-07-11 | 1342314 | Customer |  | Starlink — ERP SpaceX | Starlink | Jonh dusk | elon@tesla.com | 1222333444 | SpaceX |  | erp | 1342314 | SJC — San Jose | SJC — San Jose | 2 | Wave 1 | 95 | FLEX Ready | Large | Core | erp | Rehost | 3 | WAITING LIST |  | ERP SpaceX | erp | Critical | Production | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring | Web Frontend ¦ API Server ¦ ERP Backend ¦ Database ¦ Batch Worker ¦ Queue ¦ File Storage ¦ Reporting ¦ Monitoring
2026-07-04 | 2026-07-04 | 2026-07-11 |  | 2026-07-11 | 1342314 | Customer |  | Starlink — Amazon | Starlink | Jonh dusk | elon@tesla.com | 1222333444 | Amazon | Brian | ecommerce | 1342314 | SJC — San Jose | SJC — San Jose | 1 | Wave 1 | 95 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | WAITING LIST |  | Amazon | ecommerce | Critical | Production | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring | Web Frontend ¦ API Gateway ¦ API Server ¦ Product Catalog Backend ¦ Database ¦ Cache ¦ Queue ¦ Payment Connector ¦ Order Worker ¦ Search Service ¦ Monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | ZAIN | space X — ERP SpaceX | space X | elon musk | elon@starlink | 1222333444 |  |  | erp | 1234 | DFW — Dallas | DFW — Dallas | 2 | Wave 1 | 85 | FLEX Ready | Large | Core | erp | Rehost | 3 | ACTIVE |  | ERP SpaceX | erp |  |  | 9 | 5 component type: application, 1 component type: database, 1 component type: worker, 1 component type: queue, 1 component type: monitoring
2026-07-04 | 2026-07-05 | 2026-07-09 |  |  | 1234 | Operator | ZAIN | space X — Amazon | space X | elon musk | elon@starlink | 1222333444 |  |  | ecommerce | 1234 | DFW — Dallas | DFW — Dallas | 1 | Wave 1 | 85 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | ACTIVE |  | Amazon | ecommerce |  |  | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring
7/4/2026 | 7/5/2026 | 7/9/2026 |  |  | 1234 | Operator | dzoan | space X — Amazon | space X | elon musk | elon@starlink | 1222333444 |  |  | ecommerce | 1234 | DFW — Dallas | DFW — Dallas | 1 | Wave 1 | 85 | FLEX Ready | Large | Core | ecommerce | Rehost | 3 | ACTIVE |  | Amazon | ecommerce |  |  | 11 | 5 component type: application, 1 component type: api gateway, 1 component type: database, 1 component type: cache, 1 component type: queue, 1 component type: worker, 1 component type: monitoring