## Migration Backlog
customer_name | projet | status | Fail Cause | action | start_date | target_date | customer_id | priority_rank | flex_readiness | industry | ospc_infra_size | reference_architecture | wave | flex_readiness_score | region | business_blast_radius | stack_category | migration_method | ospc_vm_count | size_rank | os_package | runtimes | env | legacy_package | os_versions | resource_summary | resource_breakdown
RAX | OS2FLEX POC | In progress |  | Continue | 25/03/2026 | ASAP | OSPC2FLEX migration Origin POC | 1 | FLEX Ready | Internal / Cloud Migration | Medium | 2 front end, 2 back end, 3 DB, 48 total resources | Wave 0 | 100 | DFW3 | Important | Frontend + API + DB | Replatform | 7 | 2 | nginx/apache + python/java runtime + db client | Modern web/app + DB runtimes | poc / migration-lab | Minimal legacy blockers | Ubuntu 22.04 / RHEL 8/9 equivalent | 48 resources total | database_instance=15 (31.3%); block_storage_volume=9 (18.8%); cloud_server=8 (16.7%); ha_database_group=4 (8.3%); database_backup=3 (6.3%)
GlobeX SaaS Cloud |  | In progress |  | Continue | 2026-03-01 | 2026-03-31 | CUST-2013 | 14 | FLEX Ready | SaaS | Medium | 2 frontend, 3 API, 1 DB, workers | Wave 4 | 87 | IAD3 | Secondary | Frontend + API + DB | Rehost | 6 | 2 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod | None / low | Ubuntu 22.04/24.04
Rex Hospitality Bookings |  | In progress |  | Continue | 2026-03-04 | 2026-04-03 | CUST-2014 | 15 | FLEX Ready | Hotels | Medium | 2 frontend, 3 backend, 1 DB, Redis | Wave 4 | 86 | ORD1 | Secondary | Headless Web App | Relocate | 7 | 2 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
Harvest Foods Vendor Portal |  | In progress |  | Continue | 2026-03-07 | 2026-04-06 | CUST-2015 | 16 | FLEX Ready | Food & Beverage | Medium | 3 app, 1 DB, 1 replica | Wave 4 | 85 | DFW3 | Secondary | Django / PostgreSQL | Rehost | 5 | 2 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022
BrightGov Permit Portal |  | In progress |  | Continue | 2026-03-10 | 2026-04-09 | CUST-2016 | 17 | FLEX Ready | Government | Medium | 2 web, 2 app, 1 DB, LB | Wave 4 | 84 | IAD3 | Secondary | Modern Web App | Rehost | 5 | 2 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / controlled | None / low | Ubuntu 22.04/24.04
Stark Logistics TMS |  | In progress |  | Continue | 2026-03-13 | 2026-04-12 | CUST-2017 | 18 | FLEX Ready | Logistics | Medium | 2 frontend, 4 backend, 1 DB, Redis | Wave 5 | 83 | ORD1 | Important | N-tier Web App | Relocate | 8 | 2 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
Helio Manufacturing MES |  | In progress |  | Continue | 2026-03-16 | 2026-04-15 | CUST-2018 | 19 | FLEX Ready | Manufacturing | Medium | 3 app, 1 DB primary, 1 replica | Wave 5 | 82 | DFW3 | Important | Java App + DB | Rehost | 8 | 2 | JDK + app server + db client | Java 17 / Spring Boot / Tomcat | prod | None / low | RHEL 8/9 or Ubuntu 22.04
Nova Health App Platform |  | In progress |  | Continue | 2026-03-19 | 2026-04-18 | CUST-2019 | 20 | FLEX Ready | Healthcare | Medium | 3 API, 2 workers, 1 DB | Wave 5 | 81 | IAD3 | Important | API + Worker + DB | Replatform | 9 | 2 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / regulated | None / low | Ubuntu 22.04/24.04
Atlas Retail OMS |  | In progress |  | Continue | 2026-03-22 | 2026-04-21 | CUST-2020 | 21 | FLEX Ready | Retail | Medium | 2 frontend, 4 API, search, Redis | Wave 5 | 80 | ORD1 | Important | Headless Commerce | Replatform | 10 | 2 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
Massive Dynamic ERP Lite |  | In progress |  | Continue | 2026-03-25 | 2026-04-24 | CUST-2021 | 22 | FLEX Ready | Enterprise IT | Medium | 3 app, 1 DB primary, 1 replica | Wave 6 | 79 | DFW3 | Core | IIS / App / SQL | Relocate | 8 | 2 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022
Beacon Bank Treasury |  | In progress |  | Continue | 2026-03-28 | 2026-04-27 | CUST-2022 | 23 | FLEX Ready | Banking | Medium | 4 API, 1 DB, Redis | Wave 6 | 78 | IAD3 | Core | API + DB + Cache | Replatform | 9 | 2 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / regulated | None / low | Ubuntu 22.04/24.04
OrbitAir Revenue Core |  | In progress |  | Continue | 2026-03-31 | 2026-04-30 | CUST-2023 | 24 | FLEX Ready | Airlines | Medium | 3 app, 1 DB, worker tier | Wave 6 | 77 | ORD1 | Core | Java / PostgreSQL | Replatform | 8 | 2 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022
PrimeTel Billing |  | In progress |  | Continue | 2026-04-03 | 2026-05-03 | CUST-2024 | 25 | FLEX Ready | Telecom | Medium | 2 web, 3 app, 1 DB | Wave 6 | 76 | DFW3 | Core | Modern Web + DB | Relocate | 7 | 2 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
OmniMedia Streaming CMS |  | In progress |  | Continue | 2026-04-06 | 2026-05-06 | CUST-2025 | 26 | FLEX Ready | Media | Large | 4 frontend, 6 app, 2 DB, Redis | Wave 7 | 75 | IAD3 | Secondary | N-tier Media Platform | Rehost | 14 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
CampusOne Digital Learning |  | In progress |  | Continue | 2026-04-09 | 2026-05-09 | CUST-2026 | 27 | FLEX Ready | Education | Large | 4 frontend, 8 services, 2 DBs | Wave 7 | 74 | ORD1 | Secondary | Microservices Lite | Replatform | 15 | 3 | container runtime + k8s tools + csi client | Docker / Kubernetes / service runtimes | prod | Legacy container images possible | RHEL 8/9, Ubuntu 22.04, K8s-supported nodes
ShopVerse Marketplace Ops |  | In progress |  | Continue | 2026-04-12 | 2026-05-12 | CUST-2027 | 28 | FLEX Ready | Marketplace | Large | 4 frontend, 6 API, 2 DBs, search | Wave 7 | 73 | DFW3 | Secondary | Headless Commerce | Replatform | 16 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
BlueGrid Energy Portal |  | In progress |  | Continue | 2026-04-15 | 2026-05-15 | CUST-2028 | 29 | FLEX Ready | Energy | Large | K8s apps, PVs, DB, LB | Wave 7 | 72 | IAD3 | Secondary | Containerized App | Relocate | 18 | 3 | container runtime + k8s tools + csi client | Docker / Kubernetes / service runtimes | prod | Legacy container images possible | RHEL 8/9, Ubuntu 22.04, K8s-supported nodes
Mercury Commerce Core |  | In progress |  | Continue | 2026-04-18 | 2026-05-18 | CUST-2029 | 30 | FLEX Ready | E-Commerce | Large | 4 frontend, 8 API, DB primary+replicas | Wave 8 | 71 | ORD1 | Important | Headless Commerce | Replatform | 20 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
Civic Services Hub |  | In progress |  | Continue | 2026-04-21 | 2026-05-21 | CUST-2030 | 31 | FLEX Ready | Government | Large | 3 web, 6 app, 2 DBs | Wave 8 | 70 | DFW3 | Important | N-tier Citizen Services | Relocate | 18 | 3 | standard app packages + db client | Modern supported runtime | prod / controlled | Low | Ubuntu 22.04 or RHEL 8/9
Medisphere Patient Platform |  | Not started |  | START | 2026-04-22 | 2026-05-01 | CUST-2031 | 32 | FLEX Ready | Healthcare | Large | 4 API, workers, DB, cache | Wave 8 | 69 | IAD3 | Important | API + Analytics + DB | Replatform | 19 | 3 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / regulated | None / low | Ubuntu 22.04/24.04
IronWorks Supply Chain |  | Not started |  | START | 2026-04-23 | 2026-05-05 | CUST-2032 | 33 | FLEX Ready | Manufacturing | Large | 8 services, queues, DB clusters | Wave 8 | 68 | ORD1 | Important | Microservices | Replatform | 22 | 3 | container runtime + k8s tools + csi client | Docker / Kubernetes / service runtimes | prod | Legacy container images possible | RHEL 8/9, Ubuntu 22.04, K8s-supported nodes
Global Tech Industries ERP |  | Not started |  | START | 2026-04-24 | 2026-05-09 | CUST-2033 | 34 | FLEX Ready | Enterprise IT | Large | 6 app, DB cluster, LB, workers | Wave 9 | 67 | DFW3 | Core | ERP + DB Cluster | Replatform | 22 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
TitanBank Payments Hub |  | Not started |  | START | 2026-04-25 | 2026-05-13 | CUST-2034 | 35 | FLEX Ready | Banking / Payments | Large | 8 app, HA DB, Redis, MQ | Wave 9 | 66 | IAD3 | Core | Payments Platform | Replatform | 24 | 3 | standard app packages + db client | Modern supported runtime | prod / regulated | Low | Ubuntu 22.04 or RHEL 8/9
AeroNation Reservations |  | Not started |  | START | 2026-06-26 | 2026-05-17 | CUST-2035 | 36 | FLEX Ready | Airlines | Large | 6 app, DB primary+replicas, search | Wave 9 | 65 | ORD1 | Core | Reservation Platform | Replatform | 26 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
NationGrid Utility Billing |  | Not started |  | START | 2026-06-27 | 2026-05-21 | CUST-2036 | 37 | FLEX Ready | Utilities | Large | 5 app, 2 DBs, queue, cache | Wave 9 | 64 | DFW3 | Core | Billing Platform | Relocate | 20 | 3 | standard app packages + db client | Modern supported runtime | prod | Low | Ubuntu 22.04 or RHEL 8/9
Heritage Hotels PMS |  | Not started |  | START | 2026-06-28 | 2026-05-25 | CUST-2037 | 38 | Partially FLEX Ready | Hotels | Small | 2 app, 1 DB, shared files | Wave 13 | 63 | IAD3 | Secondary | Legacy LOB | Rehost -> Refactor | 2 | 1 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
PharmaLink QA |  | Not started |  | START | 2026-06-29 | 2026-05-29 | CUST-2038 | 39 | Partially FLEX Ready | Healthcare | Small | 2 app, old JVM, 1 DB | Wave 14 | 62 | ORD1 | Important | Old Java App | Relocate -> Replatform | 2 | 1 | legacy web/app packages | Mixed supported + older runtimes | prod-legacy / regulated | Moderate | Ubuntu 18.04/20.04, RHEL 7/8, Windows 2016
TownBank Branch Ops |  | Not started |  | START | 2026-06-30 | 2026-06-02 | CUST-2039 | 40 | Partially FLEX Ready | Banking | Small | 2 IIS, 1 DB, shared storage | Wave 15 | 61 | DFW3 | Core | Legacy .NET | Relocate -> Replatform | 2 | 1 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy / regulated | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
CargoMesh Planner |  | Not started |  | START | 2026-07-01 | 2026-06-06 | CUST-2040 | 41 | Partially FLEX Ready | Logistics | Medium | 3 app, DB on same VM, files | Wave 16 | 60 | IAD3 | Secondary | Monolith | Refactor | 6 | 2 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
RetailPro Inventory |  | Not started |  | START | 2026-07-02 | 2026-06-10 | CUST-2041 | 42 | Partially FLEX Ready | Retail | Medium | 3 app, embedded DB, reports | Wave 17 | 59 | ORD1 | Important | Monolith + DB | Refactor | 7 | 2 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
FlightDesk Ops |  | Not started |  | START | 2026-07-03 | 2026-06-14 | CUST-2042 | 43 | Partially FLEX Ready | Airlines | Medium | 4 app, old integrations | Wave 18 | 58 | DFW3 | Core | Legacy LOB | Rehost -> Refactor | 7 | 2 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
CityPermit Enterprise |  | Not started |  | START | 2026-07-04 | 2026-06-18 | CUST-2043 | 44 | Partially FLEX Ready | Government | Large | 6 app, DB, file shares, workers | Wave 19 | 57 | IAD3 | Secondary | Legacy N-tier | Refactor | 15 | 3 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy / controlled | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
OmniCare Claims |  | Not started |  | START | 2026-07-05 | 2026-06-22 | CUST-2044 | 45 | Partially FLEX Ready | Insurance | Large | 8 app, DB cluster, files | Wave 20 | 56 | ORD1 | Important | Monolith ERP | Refactor | 18 | 3 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
Federal Ledger |  | Not started |  | START | 2026-07-06 | 2026-06-26 | CUST-2045 | 46 | Partially FLEX Ready | Government / Finance | Large | 8 app, DB cluster, MQ | Wave 21 | 55 | DFW3 | Core | ERP Monolith | Replatform | 20 | 3 | mixed legacy app packages + db client | Older Java / .NET / PHP mixed | prod-legacy / controlled | High legacy coupling | RHEL/CentOS 7, Windows Server 2012/2016, mixed
GlobalSaaS Multi-Region |  | Not started |  | START | 2026-07-07 | 2026-06-30 | CUST-2046 | 47 | Partially FLEX Ready | SaaS | Very Large / Highly Interconnected | 20 services, PVs, search, MQ | Wave 22 | 54 | IAD3 | Secondary | Microservices + Stateful | Replatform | 30 | 4 | container runtime + legacy storage plugins | Mixed runtimes across services | prod-hybrid | Old images / old CSI / custom agents | Mixed Linux versions
TransWorld Commerce Mesh |  | Not started |  | START | 2026-07-08 | 2026-07-04 | CUST-2047 | 48 | Partially FLEX Ready | Marketplace | Very Large / Highly Interconnected | 25 services, DB domains, cache, queues | Wave 23 | 53 | ORD1 | Important | Distributed Commerce | Replatform | 32 | 4 | legacy web/app packages | Mixed supported + older runtimes | prod-legacy | Moderate | Ubuntu 18.04/20.04, RHEL 7/8, Windows 2016
MegaBank Risk Platform |  | Not started |  | START | 2026-07-09 | 2026-07-08 | CUST-2048 | 49 | Partially FLEX Ready | Banking | Very Large / Highly Interconnected | 20 app, DB domains, MQ, analytics | Wave 24 | 52 | DFW3 | Core | Enterprise Platform | Refactor -> Replatform | 35 | 4 | legacy web/app packages | Mixed supported + older runtimes | prod-legacy / regulated | Moderate | Ubuntu 18.04/20.04, RHEL 7/8, Windows 2016
ArchiveDocs Legacy |  | Not started |  | START | 2026-07-10 | 2026-07-12 | CUST-2049 | 50 | Not Yet FLEX Ready | Legal Services | Small | 1 app, local files, Windows 2008 | Wave 25 | 51 | IAD3 | Secondary | Old Windows App | Retain / Replace | 1 | 1 | legacy Windows app stack | .NET Framework / old IIS / local services | legacy-prod | High | Windows Server 2008/2012
ClassicERP Light |  | Not started |  | START | 2026-07-11 | 2026-07-16 | CUST-2050 | 51 | Not Yet FLEX Ready | Manufacturing | Small | 1 app, 1 DB, old OS | Wave 26 | 50 | ORD1 | Important | Old ERP | Replatform / Replace | 1 | 1 | obsolete app packages + db client | Old Java / old PHP / old app server | legacy-prod | Very high | RHEL 6/7, CentOS 6/7, Ubuntu 16.04/18.04, mixed
BranchCore 2008 |  | Not started |  | START | 2026-07-12 | 2026-07-20 | CUST-2051 | 52 | Not Yet FLEX Ready | Banking | Small | 1 app, local DB, Windows 2008 | Wave 27 | 49 | DFW3 | Core | Legacy Windows Core | Retain / Replatform | 1 | 1 | legacy Windows app stack | .NET Framework / old IIS / local services | legacy-prod / regulated | High | Windows Server 2008/2012
PlantOps Classic |  | Not started |  | START | 2026-07-13 | 2026-07-24 | CUST-2052 | 53 | Not Yet FLEX Ready | Manufacturing | Medium | 3 app, old DB, SMB shares | Wave 28 | 48 | IAD3 | Secondary | Old LOB | Refactor / Replace | 4 | 2 | obsolete app packages + db client | Old Java / old PHP / old app server | legacy-prod | Very high | RHEL 6/7, CentOS 6/7, Ubuntu 16.04/18.04, mixed
MediArchive Imaging |  | Not started |  | START | 2026-07-14 | 2026-07-28 | CUST-2053 | 54 | Not Yet FLEX Ready | Healthcare | Medium | appliance VM, proprietary storage | Wave 29 | 47 | ORD1 | Important | Xen-bound Appliance | Retain / Integrate | 5 | 2 | vendor appliance / proprietary stack | Vendor runtime / proprietary services | legacy-prod / regulated | Critical proprietary package set | Appliance OS / mainframe / proprietary
AirOps Legacy Dispatch |  | Not started |  | START | 2026-07-15 | 2026-08-01 | CUST-2054 | 55 | Not Yet FLEX Ready | Airlines | Medium | 4 app, DB embedded, files | Wave 30 | 46 | DFW3 | Core | Old Monolith | Refactor / Replatform | 6 | 2 | obsolete app packages + db client | Old Java / old PHP / old app server | legacy-prod | Very high | RHEL 6/7, CentOS 6/7, Ubuntu 16.04/18.04, mixed
GovRecords Archive |  | Not started |  | START | 2026-07-16 | 2026-08-05 | CUST-2055 | 56 | Not Yet FLEX Ready | Government | Large | 6 app, old storage, reports | Wave 31 | 45 | IAD3 | Secondary | Legacy Archive Stack | Retire / Archive | 12 | 3 | legacy mixed packages | Unsupported / mixed runtime | legacy-prod / controlled | Very high | Mixed obsolete OS
MegaRetail Legacy Commerce |  | Not started |  | START | 2026-07-17 | 2026-08-09 | CUST-2056 | 57 | Not Yet FLEX Ready | Retail | Large | 8 app, old search, old DB | Wave 32 | 44 | ORD1 | Important | Old Commerce Stack | Replace / Replatform | 16 | 3 | obsolete app packages + db client | Old Java / old PHP / old app server | legacy-prod | Very high | RHEL 6/7, CentOS 6/7, Ubuntu 16.04/18.04, mixed
NationalClaims Main Core |  | Not started |  | START | 2026-07-18 | 2026-08-13 | CUST-2057 | 58 | Not Yet FLEX Ready | Insurance | Large | 10 app, old DB, file shares | Wave 33 | 43 | DFW3 | Core | Custom Main App | Refactor / Replatform | 18 | 3 | legacy mixed packages | Unsupported / mixed runtime | legacy-prod | Very high | Mixed obsolete OS
ReportHub Legacy Estate |  | failed | compatibility issues | Review | 2026-07-19 | 2026-08-17 | CUST-2058 | 59 | Not Yet FLEX Ready | Enterprise IT | Very Large / Highly Interconnected | many VMs, ETL, reports, shares | Wave 34 | 42 | IAD3 | Secondary | Legacy Reporting Estate | Retire / Archive | 20 | 4 | legacy mixed packages | Unsupported / mixed runtime | legacy-prod | Very high | Mixed obsolete OS
OracleNation Legacy Mesh |  | failed | compatibility issues | Review | 2026-07-20 | 2026-08-21 | CUST-2059 | 60 | Not Yet FLEX Ready | Enterprise IT | Very Large / Highly Interconnected | many VMs, vendor apps, shared DBs | Wave 35 | 41 | ORD1 | Important | Vendor COTS Estate | Replace / Integrate | 28 | 4 | legacy mixed packages | Unsupported / mixed runtime | legacy-prod | Very high | Mixed obsolete OS
CoreMainframe Connect |  | failed | compatibility issues | Review | 2026-07-21 | 2026-08-25 | CUST-2060 | 61 | Not Yet FLEX Ready | Banking / Mainframe | Very Large / Highly Interconnected | mainframe feeds, ETL to FLEX only | Wave 36 | 40 | DFW3 | Core | Mainframe / Appliance | Retain / Integrate | 40 | 4 | vendor appliance / proprietary stack | Vendor runtime / proprietary services | legacy-prod / regulated | Critical proprietary package set | Appliance OS / mainframe / proprietary
BlueLeaf Marketing |  | Finished |  | Monitor | 2026-01-10 | 2026-01-31 | CUST-2001 | 2 | FLEX Ready | Retail / SMB Web | Small | 2 frontend, 2 backend, 1 DB, 1 LB | Wave 1 | 99 | DFW3 | Secondary | WordPress / LAMP | Rehost | 2 | 1 | nginx/apache + php-fpm + db client | PHP 8.x | prod | Minimal legacy modules | Ubuntu 20.04/22.04 or RHEL 8/9
Silver Pine Clinics |  | Finished |  | Monitor | 2026-01-12 | 2026-02-02 | CUST-2002 | 3 | FLEX Ready | Healthcare | Small | 2 app, 1 DB, 1 LB | Wave 1 | 98 | ORD1 | Secondary | Modern Web App | Rehost | 3 | 1 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / regulated | None / low | Ubuntu 22.04/24.04
NorthDock Logistics Portal |  | Finished |  | Monitor | 2026-01-14 | 2026-02-04 | CUST-2003 | 4 | FLEX Ready | Logistics | Small | 2 frontend, 2 API, 1 DB | Wave 1 | 97 | IAD3 | Secondary | Frontend + API + DB | Relocate | 3 | 1 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod | None / low | Ubuntu 22.04/24.04
Vista Legal Forms |  | Finished |  | Monitor | 2026-01-16 | 2026-02-06 | CUST-2004 | 5 | FLEX Ready | Legal Services | Small | 2 web, 1 DB, 1 LB | Wave 1 | 96 | DFW3 | Secondary | Drupal / PHP | Rehost | 2 | 1 | nginx/apache + php-fpm + db client | PHP 8.x | prod | Minimal legacy modules | Ubuntu 20.04/22.04 or RHEL 8/9
Acme E-Commerce |  | Finished |  | Monitor | 2026-01-18 | 2026-02-08 | CUST-2005 | 6 | FLEX Ready | E-Commerce | Small | 2 frontend, 3 backend, 1 DB, Redis | Wave 2 | 95 | IAD3 | Important | Magento / LEMP | Rehost | 4 | 1 | nginx/apache + php-fpm + db client | PHP 8.x | prod | Minimal legacy modules | Ubuntu 20.04/22.04 or RHEL 8/9
CedarEdu LMS |  | Finished |  | Monitor | 2026-01-20 | 2026-02-10 | CUST-2006 | 7 | FLEX Ready | Education | Small | 2 web, 2 app, 1 DB | Wave 2 | 94 | ORD1 | Important | Laravel / MySQL | Rehost | 3 | 1 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022
GreenLine Insurance Claims |  | Finished |  | Monitor | 2026-01-22 | 2026-02-12 | CUST-2007 | 8 | FLEX Ready | Insurance | Small | 2 app, 1 DB, 1 LB | Wave 2 | 93 | DFW3 | Important | Spring Boot + PostgreSQL | Relocate | 3 | 1 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022
Metro Auto Dealer Hub |  | Finished |  | Monitor | 2026-01-24 | 2026-02-14 | CUST-2008 | 9 | FLEX Ready | Automotive | Small | 2 app, Redis, 1 DB | Wave 2 | 92 | IAD3 | Important | Node.js + Redis | Rehost | 3 | 1 | nodejs + nginx + db/redis client | Node.js 20 LTS | prod | None / low | Ubuntu 22.04/24.04
Wayne Financial Mobile API |  | Finished |  | Monitor | 2026-01-26 | 2026-02-16 | CUST-2009 | 10 | FLEX Ready | Banking / Fintech | Small | 2 API, 1 DB primary, 1 replica | Wave 3 | 91 | DFW3 | Core | API + PostgreSQL | Replatform | 3 | 1 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod / regulated | None / low legacy dependency | Windows Server 2019/2022
SkyTel Identity Service |  | Finished |  | Monitor | 2026-01-28 | 2026-02-18 | CUST-2010 | 11 | FLEX Ready | Telecom | Small | 2 app, 1 DB, 1 LB | Wave 3 | 90 | ORD1 | Core | Java API / DB | Replatform | 2 | 1 | JDK + app server + db client | Java 17 / Spring Boot / Tomcat | prod | None / low | RHEL 8/9 or Ubuntu 22.04
UrbanPay Settlement API |  | Finished |  | Monitor | 2026-01-30 | 2026-02-20 | CUST-2011 | 12 | FLEX Ready | Payments | Small | 2 app, 1 DB, Redis | Wave 3 | 89 | IAD3 | Core | Modern API Stack | Replatform | 3 | 1 | python3 + gunicorn/uvicorn + nginx | Python 3.11 | prod / regulated | None / low | Ubuntu 22.04/24.04
AeroOps Crew Portal |  | Finished |  | Monitor | 2026-02-01 | 2026-02-22 | CUST-2012 | 13 | FLEX Ready | Airlines | Small | 2 IIS, 1 DB, 1 LB | Wave 3 | 88 | DFW3 | Core | IIS / .NET + SQL | Relocate | 2 | 1 | Windows Server base + IIS/.NET | .NET / IIS / MSSQL tools | prod | None / low legacy dependency | Windows Server 2019/2022

## Prioritization Guide
Migration prioritization model | FLEX Readiness > OSPC Infra Size / Complexity > Business Blast Radius
Readiness order | FLEX Ready -> Partially FLEX Ready -> Not Yet FLEX Ready
Size order | Small -> Medium -> Large -> Very Large / Highly Interconnected
Blast radius order | Secondary -> Important -> Core
Guardrail | No core app moves before at least 2-3 successful non-core FLEX-ready migrations are completed.
How to use this sample | Start from Wave 1 and work downward. Inside each wave, use the listed migration method by stack category.
Sample status mix | 50% Not started / 30% In progress / 20% Finished