## Migration Log
DATE ADDED TO MIGRATION LIST | START DATE | COMPLETION DATE | OSPC ACCOUNT TENANT ID | SOURCE OF REQUEST | MIGRATION OPERATOR NAME | CUSTOMER NAME | COMPANY NAME | CONTACT NAME | EMAIL | PHONE | BUSINESS OWNER | TECHNICAL OWNER | INDUSTRY | CUSTOMER ID | REGION | TARGET FLEX REGION | PRIORITY RANK | WAVE | FLEX READINESS SCORE | FLEX READINESS | OSPC INFRA SIZE | BUSINESS BLAST RADIUS | STACK CATEGORY | MIGRATION METHOD | SIZE RANK | STATUS | CURRENT STAGE | BUSINESS SYSTEM NAME | BUSINESS SYSTEM TYPE | CRITICALITY | ENVIRONMENT | OSPC VM COUNT | ARCHITECTURE
2026-07-08 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — Automatic Business System from Existing VMs | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | custom | 1342314 | SJC — San Jose | SJC — San Jose | 1 | Wave 1 | 70 | Partially FLEX Ready | Small | Core | custom | Rehost | 1 | DRAFT |  | Automatic Business System from Existing VMs | custom | Critical | Production | 3 | API Gateway — linsnap-API_Gateway_Mobile_AP-20260703-0014, Web Frontend — linsnap-bankappfrontend-20260703-0007, Database — flexpostgresql
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — credit appraisal | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 12 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | credit appraisal | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — ACB bank | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 11 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | ACB bank | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — test | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 10 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | test | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — baking | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 9 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | baking | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — banking abc | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 8 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | banking abc | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — banking system | space X | elon musk | elon@starlink | +1222333444 |  |  | banking | 1234 | DFW — Dallas | DFW — Dallas | 7 | Wave 1 | 85 | FLEX Ready | Large | Core | banking | Rehost | 3 | ACTIVE |  | banking system | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — CRM | space X | elon musk | elon@starlink | +1222333444 |  |  | crm | 1234 | DFW — Dallas | DFW — Dallas | 6 | Wave 1 | 85 | FLEX Ready | Large | Core | crm | Rehost | 3 | ACTIVE |  | CRM | crm | Critical | Production | 9 | Web Frontend, API Server, Backend App Server, Database, Cache, File Storage, Reporting, Integration API, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — SAAS | space X | elon musk | elon@starlink | +1222333444 |  |  | saas | 1234 | DFW — Dallas | DFW — Dallas | 5 | Wave 1 | 85 | FLEX Ready | Large | Core | saas | Rehost | 3 | ACTIVE |  | SAAS | saas | Critical | Production | 7 | Web Frontend, API Server, Backend App Server, Database, Cache, Worker, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — data warehouse | space X | elon musk | elon@starlink | +1222333444 |  |  | data | 1234 | DFW — Dallas | DFW — Dallas | 4 | Wave 1 | 85 | FLEX Ready | Large | Core | data | Rehost | 3 | ACTIVE |  | data warehouse | data | Critical | Production | 7 | Ingestion Endpoint, Database, Object Storage, Worker, Queue, Scheduler, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — worker | space X | elon musk | elon@starlink | +1222333444 |  |  | batch | 1234 | DFW — Dallas | DFW — Dallas | 3 | Wave 1 | 85 | FLEX Ready | Medium | Core | batch | Rehost | 2 | ACTIVE |  | worker | batch | Critical | Production | 6 | Worker, Queue, Database, File Storage, Scheduler, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — BI | space X | elon musk | elon@starlink | +1222333444 |  |  | reporting | 1234 | DFW — Dallas | DFW — Dallas | 2 | Wave 1 | 85 | FLEX Ready | Medium | Core | reporting | Rehost | 2 | ACTIVE |  | BI | reporting | Critical | Production | 6 | Reporting App, Database, File Storage, Scheduler / Worker, Export Service, Monitoring
2026-07-07 | 2026-07-05 | 2026-07-12 | 1234 | Operator | Zain | space X — ERP SpaceX | space X | elon musk | elon@starlink | +1222333444 |  |  | erp | 1234 | DFW — Dallas | DFW — Dallas | 1 | Wave 1 | 85 | FLEX Ready | Large | Core | erp | Rehost | 3 | ACTIVE |  | ERP SpaceX | erp | Critical | Production | 9 | Web Frontend, API Server, ERP Backend, Database, Batch Worker, Queue, File Storage, Reporting, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — ABC | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 8 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | ABC | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — credit appraisal | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 7 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | credit appraisal | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — ACB bank | home depot | jack builder | jack@homedepot.com | +84793215913 | tien |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 6 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | ACB bank | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — test | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 5 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | test | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — baking | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 4 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | baking | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — banking abc | home depot | jack builder | jack@homedepot.com | +84793215913 | Tesla |  | banking | 1342314 | SJC — San Jose | SJC — San Jose | 3 | Wave 1 | 95 | FLEX Ready | Large | Core | banking | Rehost | 3 | WAITING LIST |  | banking abc | banking | Critical | Production | 11 | Web Frontend, API Gateway, API Server, Core Banking Backend, Database, Cache, Queue, Worker, Reporting, Auth / SSO, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — BI | home depot | jack builder | jack@homedepot.com | +84793215913 |  |  | reporting | 1342314 | SJC — San Jose | SJC — San Jose | 2 | Wave 1 | 95 | FLEX Ready | Medium | Core | reporting | Rehost | 2 | WAITING LIST |  | BI | reporting | Critical | Production | 6 | Reporting App, Database, File Storage, Scheduler / Worker, Export Service, Monitoring
2026-07-07 | 2026-07-04 | 2026-07-10 | 1342314 | Customer |  | home depot — ERP SpaceX | home depot | jack builder | jack@homedepot.com | +84793215913 | SpaceX |  | erp | 1342314 | SJC — San Jose | SJC — San Jose | 1 | Wave 1 | 95 | FLEX Ready | Large | Core | erp | Rehost | 3 | WAITING LIST |  | ERP SpaceX | erp | Critical | Production | 9 | Web Frontend, API Server, ERP Backend, Database, Batch Worker, Queue, File Storage, Reporting, Monitoring